## Slide 1
Software engineering (Undergraduate)
Course Name software Development project management
CSC 4125
(Undergraduate)
Chapter 3 process framework
M. Mahmudul hasan
Assistant Professor, CS, AIUB
http://www.dit.hua.gr/~m.hasan

## Slide 2: Introduction
All of the work that is done on a project is made up of processes
There is a pattern to all of the work that gets done on the project
    Plan
    Work
    - Compare with the original plan - If off-plan, corrections are made and everything needs to get back on track
Process framework, Process groups, and Knowledge areas ensures project smoothness.

## Slide 3: Process groups (PMBOK)
Process Groups are the steps of a project
Needs: Scope
Initiation: Requirements and System Analysis
Planning: Estimation and Resource Allocation
Execution: Implementation
Monitoring and Controlling: Track progress, adjust as required
Closing: Successful completion of the project
If the project is really big, then it can be managed in Phases
Each phase of the project goes through all five process groups

## Slide 4: Process phase relationships
Sequential Phase Relationship
  When a project has sequential phases, each phase starts after the previous phase is 100% complete
Overlapping Phase Relationship
  Sometimes teams need to work independently on different parts of the project, so that one team delivers their results while another team is still working
Iterative Phase Relationship
  A project got a single team performing the Initiating and Planning Processes for one phase, while also doing the Executing processes for the previous phase. That way, when the Executing and Closing process groups are finished, the team can jump straight into the next phase’s Executing processes.

## Slide 5: pmbok
Within each process group there are several individual processes that define how actually the work is done in the project
The PMBOK breaks every project down into 49 processes
Each of the processes belongs to only one process groups
  Project
  Management
  Body
  Of
  Knowledge

## Slide 6: Pmbok (some of the 49 processes)
Needs and Initiating Process Groups: (only 2 processes)
  Develop Project Charter (agreement)
  Identify Stakeholders
Planning Process Groups: (24 processes)
  Develop Project Management Plan
  Identify Risks
  Plan Quality
  Estimate Activity Durations
  …

## Slide 7: Pmbok (some of the 49 processes)
Executing Process Groups: (10 processes)
  Direct & Manage Project Execution
  Distribute Information
  …
Monitoring and Controlling Process Groups: (12 processes)
  Control Scope
  Monitor and Control Project Work
  Control Schedule
Close Project (1 process)

## Slide 8: Anatomy of processes
Input
  Information that are used in the project
Tools and Techniques
  Takes inputs and turns them into outputs
  All project work
Outputs
  Documents, Deliverables, and Decisions
  Helps project come in on time, within budget, and high quality
Process
(Req. Analysis)
Stakeholder
Document
Project Skills
Requirement Specification Document (SRS)
Input
Output

## Slide 9: Anatomy of processes
Sometimes the output of one process becomes an input of the next process
The process groups help in organizing the processes by the kind of work that is done
The knowledge areas help in organizing by the subject matter that’s being dealt with
  The processes are organized in two ways – the process groups are about how you do the work, and the knowledge areas are there to help you categorize them and help you learn

## Slide 10: PMBOK’s Knowledge Areas
1. Integration Management
  Making sure all the right parts of the project come together in the right order, at the right time
  Coordinating all of the work so that it happens correctly. Making sure changes are approved before they happen
2. Scope Management
  Figuring out what work needs to be done for your project. Making sure your end product has everything you said it would.
  Scope of timebox to build the system functionality

## Slide 11: PMBOK’s Knowledge Areas
3. Time Management
  Preparation and Implementation time
  Figuring out the time it will take to do your work and the order you need to do it in. Tracking your schedule and making sure everything gets done on time
4. Cost Management
  Budgeting for the project
  Knowing how much you’re able to invest in the project and making sure you spend it right
5. Quality Management
  Making sure that output maintains standard
  Making sure you work as efficiently as you can and don’t add defects into the product

## Slide 12: PMBOK’s Knowledge Areas
6. Human Resource Management
  Efficient use of schedules. Getting the people to work on the team and helping them stay motivated. Rewarding them for a job well done and resolving conflicts that come up
7. Communications Management
  Making sure that consistent communications are maintained
  Making sure that everybody knows what they need to know to do the job right. Tracking how people talk to each other and dealing with gaps if they happen
8. Risk Management
  Figuring out how to protect your project from anything unusual that could happen to it
  Risk Management can also be about making sure that you are in the right position to take advantage of the opportunities that come your way

## Slide 13: PMBOK’s Knowledge Areas
9. Procurement Management
  Selecting the right source for resources
  Finding contractors to help you do the work. Setting the ground rules for their relationships with your company
10. Stakeholder Management
  Identify the people, groups, or organizations that could impact or be impacted by the project
  Analyze stakeholder expectations and develop appropriate management strategies for effectively engaging stakeholders in project decisions and execution

## Slide 14: Process group vs. Knowledge Areas
Process groups and Knowledge Areas are two different ways to organize the processes but they don’t really overlap each other!
Process groups divide up the processes by function
Knowledge areas divide the same processes by subject matter
Every process belong to exactly one process group
Every process is in exactly one knowledge area

## Slide 15: references
Bob Hughes and Mike Cotterel (1999). Software Project Management (Second Edition).
PMBOK Guide: Project Lifecycle (5th Edition)
MMH