## Slide 1
Software engineering (Undergraduate)
Course Name software Development project management
CSC 4125
(Undergraduate)
Chapter 8 resource allocation
M. Mahmudul hasan
Assistant Professor, CS, AIUB
http://www.dit.hua.gr/~m.hasan

## Slide 2: Resource allocation
Plan the activity with available resources and, where necessary, asses the efficacy of changing the plan to fit the resources.
The allocation of resources to activities will lead us to review and modify the ideal activity plan, it may cause us to revise stage or project completion date.
The result of resource allocation will normally be several schedules including:
  Activity schedule: indicating the planned start and completion dates for each activity
  Resource schedule: indicating the dates when resources will be required and the level of required resources
  Cost schedule: showing the planned accumulative expenditure incurred by the use of resources over time
MMH

## Slide 3: The nature of Resource
A resource is any item or person required for the execution of the project. This covers many things – from the paper clips to key personnel
In general, resource will fall into one of seven categories:
Labour: members of the development team such as the project manager, system analyst
Equipment: obvious items include workstations and other computing and office equipment such as desks and chairs (physical resource shared among multiple projects)
Materials: materials are items that are consumed, rather than equipment that is used. Software that is widely distributed might, for example, require supplies of CDs to be specially obtained.
Space: for project that are undertaken with existing staff, office space is normally readily available. If any additional staff (recruited or contracted) should be needed then office space will need to be found.
MMH

## Slide 4: The nature of Resource
Services: some projects will require procurement of specialist services, for example, requires scheduling of telecommunication services.
Time: time is the resource that is being offset (balance) against the other primary resources. Project time-scales can sometimes be reduced by increasing other resources (e.g. staff).
Money: money is a secondary resource, it is used to buy other resources and will be consumed as other resources are used.
MMH

## Slide 5: Resource allocation
Identify the resources needed for each activity
Identify resource types - individuals are interchangeable within the group (e.g. ‘VB programmers’ as opposed to ‘software developers’)
Allocate resource types to activities and examine the resource histogram
WEEK
1
2
3
4
5
6
7
1
2
3
4
5
STAFF REQD.
MMH

## Slide 6: Resource clashes
can be resolved by:
delaying one of the activities
  taking advantage of float to change start date
  delaying start of one activity until finish of the other activity that resource is being used on - puts back project completion
moving resource from a non-critical activity
bringing in additional resource - increases costs
MMH

## Slide 7: Prioritizing activities
There are two main ways of doing this:
Total float priority: those with the smallest float have the highest priority
Ordered list priority: this takes account of the duration of the activity as well as the float
Burman’s priority list:
1. Shortest critical activities (no float, small duration)
2. Other critical activities (no float, other duration)
3. Shortest non-critical activities (have float, but small duration)
4. Non-critical activities with least float
5. Non-critical activities
MMH

## Slide 8: Resources usage
Need to maximize % usage of resources, i.e. reduce idle periods between tasks
Need to balance costs against early completion date (early completion may expensive)
Need to allow for contingency (a future event or circumstance that is possible but cannot be predicted with certainty)
MMH

## Slide 9: Critical path
Scheduling resources can create new dependencies between activities (critical path). Delaying the start of an activity because of lack of resources will cause that activity to become critical this uses up its float.
Furthermore, a delay in completing one activity can delay the availability of a resource required for a later activity.
MMH

## Slide 10: Allocating individuals to activities
The initial ‘resource types’ for a task have to be replaced by actual individuals
Factors to be considered:
  Availability: whether a particular individual will be available when required
  Criticality: allocating of more experienced personnel to activities on the critical path often helps in shortening project durations or at least reduces the risk of overrun
  Risk: identify activities those posing the greatest risk, and know the factors influencing them. Allocating the most experienced staff to the highest risk activities is likely to have the greatest effect in reducing overall project uncertainties. More experienced staff are, however, usually more expensive.
MMH

## Slide 11: Allocating individuals to activities
Training: allocate junior staff to appropriate non-critical activities where there will be sufficient slack for them to train and develop skills. There can be direct benefits to the particular project since some costs may be allocated to the training budget.
Team building: the selection of motivated individuals must also take account of the final shape of the project team and the way they will work together.
MMH

## Slide 12: Cost schedule
Showing weekly and monthly costs over the life of the project. This will provide more detailed and accurate estimate of costs.
In general, costs are categories as follows:
Staff costs: includes staff salaries, employer’s contribution to social security funds, pension, holiday pay, and sickness benefit.
Overheads: expenditure that an organization incurs, which cannot be directly related to individual projects such as rental office space.
Usage charges: In some organization, projects are charged directly for use of resources such as computer time, bandwidth, etc. (rather than their cost being recovered as an overhead). This is normally be on ‘as used’ basis.
MMH

## Slide 13: Balancing concerns
Slide-13
MMH

## Slide 14: references
Bob Hughes and Mike Cotterel (1999). Software Project Management (Second Edition).
PMBOK Guide: Project Lifecycle (5th Edition)
MMH